## Project Status
Project Northstar status
Sample data for the Work IQ exercise ¦ Reporting date: 6 September 2026
Work item | Owner | Status | Completed | Target | Due date | Latest note
Acceptance testing | Product team | In progress | 12 | 15 | 2026-09-08 | 12 of 15 scenarios passed on 5 September
Employee FAQ | Content team | Ready for review | 1 | 1 | 2026-09-08 | Revised FAQ is ready for review
Pilot welcome page | Communications team | Complete | 1 | 1 | 2026-09-05 | Content review passed
Accessibility review | Quality team | At risk | 12 | 15 | 2026-09-09 | Three keyboard-navigation issues remain open
Pilot start decision | Project sponsor | Blocked | 0 | 1 | 2026-09-10 | Waiting for accessibility review